## Customer Checklist
Verizon Solution
Task # | Customer Responsibilities | Task Completed (Y/N) | IPIA | IPT | Verizon Professional Services ("PS") Available for a Fee (see PS tab for more details)
VoIP Pre-Activation Checklist
1 | Have a detailed understanding of your current voice environment and your desired future voice environment. |  | X | X | SIP Transformation Workshop
2 | Evaluate existing LAN bandwidth to ensure it can support additional voice traffic. It is recommended that peak link utilization be below 75 percent or voice quality may be affected. |  | X | X | Network Readiness Assessment
3 | Audit all telephone numbers from all of your telephone bills to determine which ones are to be ported to Vz VoIP. Provide the Billing Telephony Number(s) for all telephone numbers to be ported to Vz VoIP. |  | X | X | SIP Transformation Services
4 | Provide all existing hunt group configurations that you want maintained after the migration to Verizon VoIP including the DIDs or extenstion numbers in the hunt groups and the hunting algorithm. |  | X | X | SIP Transformation Services
5 | Provide your inter-location dial plan requirements only if you want Verizon to host your inter-location dial plan (e.g., extension dialing). |  | X | X | SIP Transformation Services
6 | Provide Verizon with the number of digits that your phone system will be sending and expects to receive. Specifically: - For inbound calls, how many Called Number digits (e.g., 4, 7, 10) does the PBX expect to receive? - For outbound calls, how many Calling Number/ANI digits (e.g., 0, 4, 7, 10) will be sent? - If the Calling Number/ANI is not sent, what Calling # should Verizon use for all outbound calls? |  | X | X | SIP Transformation Services
7 | Identify the correct signaling interface to your phone system (Analog/CAS/PRI). - For an analog interface (e.g., Key System), Verizon supports FXS Loop Start and Ground Start signaling. Note that the analog interface must be able to accept 40 VRMS ring voltage. Specify whether Loop or Ground Start signaling is needed. - For a T1 Channel Associated Signaling ("CAS") interface, Verizon only supports Wink Start signaling. The T1 CAS interface card must be able to support this. Specify the type of framing (ESF or SF) and the type of line coding (B8ZS or AMI). - For an ISDN PRI interface, Verizon supports multiple PRI switch protocols. Specify the switch type (NI2, 5ESS, 4ESS, DMS100, Primary-NI) and which channel is being used for D-channel signaling (e.g., channel 24). |  | X |  | SIP Transformation Services
8 | Install and configure any routers, VoIP gateways, Session Border Controllers ("SBCs"), or any other Customer Premise Equipment ("CPE") not being purchased from and/or configured by Verizon as part of the solution. All configurations should conform to Verizon VoIP requirements. IP Trunking configurations should also conform to the IP-PBX vendor's SIP trunking Application Notes. Note: Even with CPE being purchased from Verizon, you should confirm with your account team whether everything will be handled by Verizon or if you will be required to perform any part of the installation(s) and/or configuration(s) of CPE. |  | X | X | SIP Transformation Services, SBC Endpoints Deployment, Verizon Onsite Services
9 | Be prepared to connect your phone system to the VoIP gateway/Integrated Access Device ("IAD") during activation testing, perhaps temporarily, and then permanently at the time of cutover as follows: - For digital signaling interfaces (PRI or CAS), connect one or more T1/DS1 crossover cables (customer provided) between the appropriate T1/DS1 ports on the VoIP gateway/IAD and the appropriate T1/DS1 ports on your phone system (distance should not exceed 133 feet). - For analog signaling interfaces, Verizon will connect either an Amphenol cable or RJ11 cables between the appropriate Amphenol RJ21X port or FXS/FXO ports on the VoIP gateway/IAD to a customer-provided 66 punch-down block or the phone system itself as long as the 66 block or phone system is in the same room as the VoIP gateway/IAD. You are responsible for all other wiring. - For converged voice and data service, also connect a CAT 5 Ethernet cable between the Ethernet port on the VoIP gateway/IAD and your LAN (distance should not exceed 50 feet). |  | X |  | Verizon Onsite Services
10 | Schedule time with your PBX vendor to participate in both the VoIP activation and the Telephone Number port to perform any necessary work on your PBX. Work examples: routing changes, SIP trunking configuration, PRI configuration changes. |  | X | X | SIP Transformation Services
11 | Ensure that your phone system is configured to handle inbound calls to every Verizon VoIP DID (new or ported) without causing any of the calls to be routed back out to the PSTN (causing a looping condition). |  | X | X | SIP Transformation Services
12 | Review the Verizon contract provisions that address E911 and phone mobility. Inform your employees about the various requirements and restrictions that affect E911 access. Ensure proper ANI is sent for 911 calls i.e. the ANI represents the location of the caller and the ANI is a reachable number if the 911 PSAP operator were to call back. |  | X | X | SIP Transformation Services
13 | If your access is Internet Dedicated Service instead of Private IP, make sure your router IOS is capable of terminating an IPSec tunnel and complete the IP Justification ("IPJ") form (see IPJ tab). |  | X | X
For Reference after Installation:
** | You are responsible for maintaining and managing all CPE unless it is under management by Verizon. Certain configuration changes to your VoIP service (e.g., Call Forwarding, Call Intercept, or Caller ID display) can be made by you via the Verizon Enterprise Center - Integrated Administrative Console. User Guides and Tutorials are available at our Customer Training and Documentation website (http://customertraining.verizon.com). Verizon can also assist you with configuration changes to your VoIP service for a fee by contacting Verizon VoIP Premium Services, 877-777-7176.

## Professional Services
Verizon Professional Services
SIP Transformation Services Available through Verizon Professional Services
Migration to IP Integrated Access
Migration to IP Trunking
Complex UC Environments
SIP Transformation
Workshop
SBC Endpoints Deployment
Facilitates transformation from distributed TDM/PRI environment to SIP trunking while continuing to use legacy PBXs or Key Systems.
Oversees migration for up to 50 locations including porting of DID numbers.
Facilitates transformation from distributed TDM/PRI environment to centralized SIP trunking for IP-enabled PBXs leveraging IP phones or existing gateways at remote locations.
Oversees migration for up to 50 locations including porting of DID numbers.
Addresses larger and more complex environments where large numbers of remote sites, other applications and services, and/or multi-vendor environments need to be integrated into a Unified Communications solution
Customized services engagement tailored to the specific requirements of each individual customer
Facilitates definition of customer specific requirements, development of strategy, evaluation and selection of CPE, and preparation and planning for migration to SIP trunking and UC services
Helps customers make informed decisions on best technologies, products, solutions, and options for their specific environment
Facilitates the installation and configuration of Session Border Controllers for IP Trunking.
Facilitates productivity enhancements through broader access to easier and better collaboration tools and services
Verizon’s SIP Transformation team can help you make this move. Our experienced engineers not only have SIP trunking expertise, but also the know how to fully integrate with all the leading UC Vendors: Cisco, Avaya, Microsoft, Oracle, Sonus, Adtran, etc.
SIP
PSTN
Applications
PBX
IM
VZ MPLS
Conferencing
Enterprises are moving away from TDM/PRI to SIP, a standard
protocol that can be used with any vendor.
Verizon Professional Services can even manage the entire project ensuring a successful outcome.
Our SIP Transformation Portfolio: Where and how can we help your business?
Functional Strategy
System Acceptance
Implementation
and Integration
Detailed Design
Operational Launch
Analysis of your existing network infrastructure and architecture to evaluate whether configurations are optimized for Voice over IP and Unified Communications (UC).
Site surveys to assess physical aspects required for supporting UC and call quality testing.
Network Readiness Assessment
Verizon Onsite Services
Verizon has technicians all across the globe that can assist with most any task.
Verizon technicians specialize in staging, installing, and integrating equipment at customer sites.